## Application Level Epics
EPIC (In Progress) | Feature/Parent User Story | UserStories | Sprint | Status | Resource | Comments | Efforts
Web POC | App Server Config and Setup | Same as Parent story | S1 | Completed | Sameer |  | 4
Web POC | Tomcat App Setup |  | S1 | Completed | Sameer |  | 4
Web POC | Java |  | S1 | Completed | Sameer |  | 4
Web POC | Linux Setup (Paths/Config/Jobs) |  | S1 | Completed | Rakesh |  | 4
Web POC | Small POC to check db connectivity with our API's |  | S1 | Completed | Rakesh |  | 9
Web POC | Development Desktops | STS Spring Tool Suite Angular CLI Angular Material Java Development Framework CI/CD - GIT, Maven, Jenkins | S1 | Completed | Rama | Set up HVD | 9
Web - Global Logon | Global Logon Onboarding | 1. Raise request form. 2. meeting with GL team. | S1 | Form has been raised waiting for the GL team to provide the domain and URL. | Rakesh/Sameer | Need to determine fields passed back from global logon - IP, desktop host name, userid, etc. These will be required for DB session tracking, user identification, ASLA logging, userid/profile compliance mangement/reporting | 18
Web - Global Logon | Global Logon Application Integration |  | S2 |  | Vaibhav |  | 50
DB Web SP - Global Logon | DB SP for Global Logon and user session establishment |  | S2 |  | Vaibhav |  | 50
Web - User Session Management | User Session Security Framework |  | S2 |  | Vaibhav |  | 50
Web - User Session Management | User Session Environment Selection |  | S2 |  | Vaibhav |  | 50
Web - User Session Management | User Session Application Selection |  | S2 |  | Vaibhav | ARMS GUI vs Report Utility web view | 50
Web - Customer Queries | Query by Customer - All | 1. Create GUI using angular. 2. Create API's. | S1 | In Progress | Rama |  | 50
Web - Customer Queries | Query by Customer - My Customers |  | S1 | In Progress | Rama |  | 50
Web - Customer Queries | Query by Customer - Account Bringups |  | S1 | In Progress | Rakesh |  | 50
Web - Customer Queries | Query by Customer - Customer Bringups |  | S1 | In Progress | Sameer |  | 50
Web - Customer Queries | Query by AECN | Create GUI. | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by OCN |  | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by CTC |  | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by Acct / Inv / Fan |  | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by ACNA |  | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by Bill Name |  | S2 | To be started | Vaibhav |  | 50
Web - Customer Queries | Query by AECN | Create API | S3 | To be started | Sameer |  | 30
Web - Customer Queries | Query by OCN |  | S3 | To be started | Sameer |  | 30
Web - Customer Queries | Query by CTC |  | S3 | To be started | Sameer |  | 30
Web - Customer Queries | Query by Acct / Inv / Fan |  | S3 | To be started | Rakesh |  | 30
Web - Customer Queries | Query by ACNA |  | S3 | To be started | Rakesh |  | 30
Web - Customer Queries | Query by Bill Name |  | S3 | To be started | Rakesh |  | 30
Web - Aged Detail | Sort | Create GUI. | S3 |  | Rama |  | 30
Web - Aged Detail | Filter |  | S3 |  | Rama |  | 30
Web - Aged Detail | Exports |  | S3 |  | Rama |  | 30
Web - Aged Detail | Invoice View |  | S3 |  | Rama |  | 30
Web - Aged Detail | Account Selections |  | S3 |  | Rama |  | 30
Web - Aged Detail | Summary Totals |  | S3 |  | Abhishaik |  | 30
Web - Aged Detail | Record Navigation / Control |  | S3 |  | Abhishaik |  | 30
Web - Customer Queries | Populate aged detail grid for AECN tab | Create API. | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for OCN tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for CTC tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for Acct/Inv/Fan tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for ACNA tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for Bill name tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate aged detail grid for Customer tab |  | S3 |  | Anil |  | 30
Web - Customer Queries | Populate query Dropdown for Customer tab |  | S3 |  | Akul |  | 30
Web - Customer Queries | Populate invoice view for AECN tab | Create API. | S3 |  | Rakesh |  | 30
Web - Customer Queries | Populate invoice view for OCN tab |  | S3 |  | Rakesh |  | 30
Web - Customer Queries | Populate invoice view for CTC tab |  | S3 |  | Rakesh |  | 30
Web - Customer Queries | Populate invoice view for Act/Inv/Fan tab |  | S3 |  | Rakesh |  | 30
Web - Customer Queries | Populate invoice view for ACNA tab |  | S3 |  | Rakesh |  | 30
Web - Customer Queries | Populate invoice view for Bill name tab |  | S3 |  | Sameer |  | 30
Web - Customer Queries | Populate invoice view for Customer tab |  | S3 |  | Anil |  | 30
Web - User Session Management | SSL/HTTPS integration on Springboot. |  | S3 |  | Rakesh |  | 30
Web - User Session Management | SSL/HTPS integration on GUI. |  | S3 |  | Rama |  | 30
Web - User Session Management | JWT and single sign on Integration in Boot. |  | S3 |  | Rakesh |  | 30
Web - User Session Management | JWT and single sign on Integration in GUI. |  | S3 |  | Rama |  | 30
Web - User Session Management | Angular Auth guard implementation |  |  |  | Vaibhav
Web - User Session Management | Logout Application |  |  |  | Vaibhav
Web - User Session Management | Implement Log4j |  |  |  | Vaibhav
Junit
Web - Aged Detail | Sort | Create API. | S4 |  | Vaibhav
Web - Aged Detail | Filter |  | S4 |  | Vaibhav
Web - Aged Detail | Exports |  | S4 |  | Vaibhav
Web - Aged Detail | Invoice View |  | S4 |  | Vaibhav
Web - Aged Detail | Account Selections |  | S4 |  | Vaibhav
Web - Aged Detail | Summary Totals |  | S4 |  | Vaibhav
Web - Aged Detail | Record Navigation / Control |  | S4 |  | Vaibhav
Web - Notes | Account Notes - Add | Create GUI. | S4 |  | Vaibhav
Web - Notes | Account Notes - Update |  | S4 |  | Vaibhav
Web - Notes | Account Notes - Delete |  | S4 |  | Vaibhav
Web - Notes | Account Notes - Display |  | S4 |  | Vaibhav
Web - Notes | Customer Notes - Add |  | S4 |  | Vaibhav
Web - Notes | Customer Notes - Update |  | S4 |  | Vaibhav
Web - Notes | Customer Notes - Delete |  | S4 |  | Vaibhav
Web - Notes | Customer Notes - Display |  | S4 |  | Vaibhav
Web - Notes | Account Notes - Add | Create API. | S5 |  | Vaibhav
Web - Notes | Account Notes - Update |  | S5 |  | Vaibhav
Web - Notes | Account Notes - Delete |  | S5 |  | Vaibhav
Web - Notes | Account Notes - Display |  | S5 |  | Vaibhav
Web - Notes | Customer Notes - Add |  | S5 |  | Vaibhav
Web - Notes | Customer Notes - Update |  | S5 |  | Vaibhav
Web - Notes | Customer Notes - Delete |  | S5 |  | Vaibhav
Web - Notes | Customer Notes - Display |  | S5 |  | Vaibhav
Web - Email | Email Details | Create GUI. | S5 |  | Vaibhav
Web - Email | Email Templates |  | S5 |  | Vaibhav
Web - Email | Email Submit |  | S5 |  | Vaibhav
Web - Contacts | Notes Entry Selections | Create GUI. | S5 |  | Vaibhav
Web - Contacts | Contacts Insert |  | S5 |  | Vaibhav
Web - Contacts | Contacts Modify |  | S5 |  | Vaibhav
Web - Contacts | Contacts Delete |  | S5 |  | Vaibhav
Web - Contacts | Contacts Account Assignment |  | S5 |  | Vaibhav
Web - Contacts | Contacts Maintenance |  | S5 |  | Vaibhav
Web - Email | Email Details | Create API. | S6 |  | Vaibhav
Web - Email | Email Templates |  | S6 |  | Vaibhav
Web - Email | Email Submit |  | S6 |  | Vaibhav
Web - Contacts | Notes Entry Selections | Create API. | S6 |  | Vaibhav
Web - Contacts | Contacts Insert |  | S6 |  | Vaibhav
Web - Contacts | Contacts Modify |  | S6 |  | Vaibhav
Web - Contacts | Contacts Delete |  | S6 |  | Vaibhav
Web - Contacts | Contacts Account Assignment |  | S6 |  | Vaibhav
Web - Contacts | Contacts Maintenance |  | S6 |  | Vaibhav
Web - Hot Notes | Hot Notes Display / Update | Create GUI | S7 |  | Vaibhav | show on app demo
Web - Preferences | User Preferences - Aged Dtl Column Order | Create GUI | S7 |  | Vaibhav | Identify dependencies and design for storing in DB
Web - Preferences | User Preferences - Bookmarks |  | S7 |  | Vaibhav | Identify dependencies and design for storing in DB
Web - Preferences | User Preferences - Template Reports |  | S7 |  | Vaibhav | Perform Analysis to determine DB vs desktop storage
Web - Preferences | User Preferences - Letter Preview |  | S7 |  | Vaibhav
Web - Preferences | User Preferences - Manual Letters |  | S7 |  | Vaibhav | Manual letters are currently saved under the desktop preferences folder. Need to consider using export/download option where user interacts with windows explorer to specify desktop location for saving the manual letters.
Web - Hot Notes | Hot Notes Display / Update | Create API | S8 |  | Vaibhav | show on app demo
Web - Preferences | User Preferences - Aged Dtl Column Order | Create API | S8 |  | Vaibhav | Identify dependencies and design for storing in DB
Web - Preferences | User Preferences - Bookmarks |  | S8 |  | Vaibhav | Identify dependencies and design for storing in DB
Web - Preferences | User Preferences - Template Reports |  | S8 |  | Vaibhav | Perform Analysis to determine DB vs desktop storage
Web - Preferences | User Preferences - Letter Preview |  | S8 |  | Vaibhav
Web - Preferences | User Preferences - Manual Letters |  | S8 |  | Vaibhav | Manual letters are currently saved under the desktop preferences folder. Need to consider using export/download option where user interacts with windows explorer to specify desktop location for saving the manual letters.
Web - Profiles | User Profile Session Tracking | Create GUI | S9 |  | Vaibhav
Web - Profiles | User Profile Management |  | S9 |  | Vaibhav
Web - Profiles | Run Default Profile |  | S9 |  | Vaibhav
Web - Notes Activity Reports | Notes Activity Reports Criteria Selection | Create GUI | S9 |  | Vaibhav
Web - Notes Activity Reports | Notes Activity Reports Display |  | S9 |  | Vaibhav
Web - Profiles | User Profile Session Tracking | Create API | S10 |  | Vaibhav
Web - Profiles | User Profile Management |  | S10 |  | Vaibhav
Web - Profiles | Run Default Profile |  | S10 |  | Vaibhav
Web - Notes Activity Reports | Notes Activity Reports Criteria Selection | Create API | S10 |  | Vaibhav
Web - Notes Activity Reports | Notes Activity Reports Display |  | S10 |  | Vaibhav
Web - User Administration | Task/Role Maintenance | Create GUI | S11 |  | Vaibhav
Web - User Administration | User Profile - Add / Modify / Delete |  | S11 |  | Vaibhav
Web - User Administration | User Reports |  | S11 |  | Vaibhav
Web - User Administration | Report Hierarchy Maintenace |  | S11 |  | Vaibhav
Web - User Administration | Task/Role Maintenance | Create API | S11 |  | Vaibhav
Web - User Administration | User Profile - Add / Modify / Delete |  | S11 |  | Vaibhav
Web - User Administration | User Reports |  | S11 |  | Vaibhav
Web - User Administration | Report Hierarchy Maintenace |  | S11 |  | Vaibhav
Web - User Documentation | Framework design | Create GUI | S12 |  | Vaibhav
Web - User Documentation | Framework design | Create API | S12 |  | Vaibhav
Table Maint tab | Xref3 Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| Xref3 history Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| Segment Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| Letter Profile Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| ACNA Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| AECN Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| Customer Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
| Message Maintenance | 1. Create GUI 2. Create API. | S13 |  | Vaibhav
Transfer Tab | Customer Transfer | 1. Create GUI 2. Create API. | S14 |  | Vaibhav
| Notes Transfer | 1. Create GUI 2. Create API. | S14 |  | Vaibhav
Management Tab | Notes Activity Report | 1. Create GUI 2. Create API. | S15 |  | Vaibhav
| Outstanding Bring up Reports | 1. Create GUI 2. Create API. | S15 |  | Vaibhav
| Payment Terms Update | 1. Create GUI 2. Create API. | S15 |  | Vaibhav
| Notes Activity Managers Report | 1. Create GUI 2. Create API. | S15 |  | Vaibhav
| Open Flag Activity Report | 1. Create GUI 2. Create API. | S15 |  | Vaibhav
Reports utility | Report Utility GUI launch Screen | 1. Create GUI 2. Create API. | S16 |  | Vaibhav

## DB Level Epics
EPIC (In Progress) | Feature/Parent User Story | UserStories | Comments | Sprint | Status | Resource | Comments | Efforts
DB POC | DB Server Config and Setup | Install all the softwares that were provided by app team |  | 1 |  | GSI |  | 4
|  | Validate all the softwares and drivers installed and accessible |  | 1 |  | App Team - Terry/Shivani |  | 15
|  | Mechid and Workgroup setup. |  | 1 | Done | SHivani |  | 9
|  | Proxies and Credentials setup |  | 1 | Done | Shivani |  | 5
|  | DB mail setup |  | 2 |  | APP/DBA | Sourav | 4
|  | SQL Login setup |  | 1 | Done | Shivani |  | 2
|  | SQL Server Job Agent Access and proxies |  | 2 |  | Shivani |  | 5
|  | Linked Server |  | 2 |  | Shivani |  | 4
|  | Create Eforcs for on-prem servers to test the connectivity Interface apps and ARMS on-pem Servers |  | 1 |  | Shivani |  | 4
|  | Share Manager - eg- import files |  | 3 |  | Shivani |  | 2
|  | Connect Direct setup and mechid access, netmap entry and access to update netmap and initparams |  |  |  | Shivani |  | 10
|  | Data router setup |  | 3 |  | Shivani |  | 5
|  | Interface connectivity |  | 2,3,4 |  | Shivani |  | 200
DB POC | Development Desktops | SQL Server Management Studio |  | 1 |  | Vaibhav |  | 2
DB POC | Driver Installation and Setup | Provide Tera data and OLE DB2 drivers to GSI team |  | 1 |  | ADBA | Saurabh | 2
|  | Install Oracle client and Oracle drivers,TeraData and OLE DB2 drivers on Pre-Prod POC env |  | 1 |  | Anupama |  | 10
|  | tnsname.ora and other configurations files to be moved from on prem to POC env |  | 1 |  | Anupama |  | 8
|  | Add System DSN's 32-bit and 64 bit using ODBC Data Source Admin from existing servers |  | 1 |  | Anupama |  | 18
|  | Validate if drivers are available in connection manager on SSDT tool |  | 1 |  | Shivani |  | 10
|  | Setup the connections for all the drivers |  | 1 |  | Shivani |  | 50
DB POC | DB Restores | ADBA provide backup from on prem servers and placse on storage account |  | 1 | Done | ADBA | Saurabh | 5
|  | GSI DBA restore DB's on Prod POC env |  | 1 | Done | Anupama |  | 3
|  | DBA to restore collection DB on Pre-prod POC env |  | 1 | Done | Anupama |  | 3
|  | DBA to restore collection investigation DB on Pre-prod POC env |  | 1 | Done | Anupama |  | 3
|  | DBA to restore SSIDB DB on Pre-prod POCnev |  | 1 | Done | Anupama |  | 3
DB POC | SSDT Setup | Create a solution and test package to test the connectivity with DB |  | 1 |  | Shivani |  | 4
|  | Test connections with all drivers ODBC, OLE, DB2 |  | 1 |  | Shivani |  | 18
|  | Copy few exisitng packages from on prem servers and perform validations and testing. |  | 2 |  | Shivani |  | 5
|  | Look for the options to export the packages from SSIS catalog |  | 2 |  | Shivani |  | 5
|  | VB library testing for load packages |  | 2 |  | Shivani |  | 10
|  | SSIS packages deployment and repository solution |  | 2 |  | Shivani |  | 18
DB POC | SQL Server Agent Jobs | Move SQL Agent Jobs from on prem server and set up on cloud. |  | 3 |  | On prem And Cloud DB
|  | Verify all the jobs are setup and scheduled as per need. |  | 3 |  | Cloud DBA/App Team
| DB Web SP - Global Logon | DB SP for Global Logon and user session establishment |  | 4 |  | App Team
| DB Web SP - User Session Management |  |  | 4 |  | App Team
| DMT packages and setup | Same as Parent Story |  | 5 |  | App Team
DB SSIS Modernization | SSIS Connection Managers Upgrade to Solution Deployment Approach | Same as Parent Story |  | 3 |  | App Team/DB team
| SSIS Deployment | Same as Parent Story |  | 3 |  | App Team/DB team
DB SP Source Management Modernization | SP GIT / DB Source Mgr integration / Setup | Same as Parent Story |  | Out of scope |  | App Team/DB Team
| SP Deployment | Same as Parent Story |  | 4 |  | App Team/DB Team
DB Web SP - Global Logon | DB SP for Global Logon and user session establishment | Idenitfy and update SP's as per plan with GUI design |  | 2 |  | App Team/DB Team
DB Web SP - User Session Management | login, logout | Idenitfy and update SP's as per plan with GUI design |  | 2 |  | App Team/DB Team
DB Web SP - Customer Queries | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 3 |  | App Team/DB Team
DB Web SP - Notes | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 4 |  | App Team/DB Team
DB Web SP - Email | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 5,6 |  | App Team/DB Team
DB Web SP - Contacts | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 5,6 |  | App Team/DB Team
DB Web SP - Ap Sub Groups | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 4 |  | App Team/DB Team
DB Web SP - Internal Contacts | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 5 |  | App Team/DB Team
DB Web SP - Payment Commitments | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 5 |  | App Team/DB Team
DB Web SP - Hot Notes | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 7 |  | App Team/DB Team
DB Web SP - Preferences | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 8 |  | App Team/DB Team
DB Web SP - Profiles | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 9 |  | App Team/DB Team
DB Web SP - Notes Activity Reports | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 9 |  | App Team/DB Team
DB Web SP - User Administration | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 11 |  | App Team/DB Team
DB Web SP - Report Utility | Idenitfy and update SP's as per plan with GUI design | Same as Parent User Story |  | 16 |  | App Team/DB Team
DB Non Prod Setup | DB Server Config and Setup |  |  | 7,8
| Driver Installation and Setup |  |  | 7,8
| DB Restores |  |  | 7,8
| SSDT Setup |  |  | 7,8
| SQL Server Agent Jobs |  |  | 9
| DMT packages and setup |  |  | 10,11
| SSIS Packages Setup and Testing |  |  | 7,8,9,10,11
| DB Web SP - Global Logon | DB SP for Global Logon and user session establishment |  | 8
| DB Web SP - User Session Management |  |  | 8
| Interface Connectivity |  |  | 7,8,9,10,11
DB PROD Setup | DB Server Config and Setup |  |  | 10,11
| Driver Installation and Setup |  |  | 10,11
| DB Restores |  |  | 10,11
| SSDT Setup |  |  | 10,11
| SQL Server Agent Jobs |  |  | 11,12
| Interface Connectivity |  |  | 15,16
| DMT packages and setup |  |  | 12,13,14
| SSIS Packages Setup and Testing |  |  | 12,13,14,15,16
| DB Web SP - Global Logon | DB SP for Global Logon and user session establishment |  | 12
| DB Web SP - User Session Management |  |  | 12

## Sprint Schedule Draft
Sprint | Start Date | End Date | Scope
Sprint 1 | 2022-01-28 | 2022-02-18 | Refer to the 1st & 2nd tab | Cutover March 18 2023,
Sprint 2 | 2022-02-18 | 2022-03-11 | Refer to the 1st & 2nd tab | MAT ends Feb 18, 2023
Sprint 3 | 2022-03-11 | 2022-04-01 | Refer to the 1st & 2nd tab | MAT starts Jan 17, 2023
Sprint 4 | 2022-04-01 | 2022-04-22 | Refer to the 1st & 2nd tab | DEV completes Dec 23, 2022 (For ARMS)
Sprint 5 | 2022-04-22 | 2022-05-13 | Refer to the 1st & 2nd tab | 50% DEV Jul 30, 2022 (As initial months would be spent in POCs, Analysis & design, requirement)
Sprint 6 | 2022-05-13 | 2022-06-03 | Refer to the 1st & 2nd tab
Sprint 7 | 2022-06-03 | 2022-06-24 | Refer to the 1st & 2nd tab
Sprint 8 | 2022-06-24 | 2022-07-15 | Refer to the 1st & 2nd tab
Sprint 9 | 2022-07-15 | 2022-08-05 | Refer to the 1st & 2nd tab
Sprint 10 | 2022-08-05 | 2022-08-26 | Refer to the 1st & 2nd tab
Sprint 11 | 2022-08-26 | 2022-09-16 | Refer to the 1st & 2nd tab
Sprint 12 | 2022-09-16 | 2022-10-07 | Refer to the 1st & 2nd tab
Sprint 13 | 2022-10-07 | 2022-10-28 | Refer to the 1st & 2nd tab
Sprint 14 | 2022-10-28 | 2022-11-18 | Refer to the 1st & 2nd tab
Sprint 15 | 2022-11-18 | 2022-12-09 | Refer to the 1st & 2nd tab
Sprint 16 | 2022-12-09 | 2022-12-30 | Refer to the 1st & 2nd tab

## Risks & Issues
SL# | Sprint | Risk/Challenge | Severity | Mitigation Plan | Owner | Target Date | Actual Resolution Date | Status
1 | 1 | Resource Onboarding | High | Additional resources are being onboarded | Management | TBD |  | In Progress
2 | 1 | Software procurement | Medium | Mitigated | Terry |  |  | Closed
SL# | Sprint | Issue |  | Resolution |  | Target Date | Actual Resolution Date | Status | Notes
1 | 1 | DB Connectivity Pending | Blocker | GSI team to work on the configuration | GSI/Dev Team | 2022-02-10 | 2022-02-08 | Closed
2 | 2 | Oracle 32 bit client installation pending | Blocker | Microsoft and GSI Team to perform the installation. | GSI/Microsoft team | 2022-02-25 | 2022-02-25 | Closed | Shivani to send a followup email to MS team 2/25 GSI team confirmed that the Oracle 32 bit client has been installed in POC env
|  | Due to Resource constraint we need to revisit the Sprint plan and move some of the DB User stories from Sprint 2 to later sprints |  | DB resource Onboarding in progress | Management/DB Team | 2022-03-28 |  | In Progress