## Development estimates
Code Impacts | Hours | Assumptions | Comments
Rewrite ARMS to web-based application using Angular 11 and Spring Boot RestAPIs. | 27000 | 1. App functionality related (Excel , Word, Browser relatd assumtions , screen changes related assumtions ,TDBGrid replacement in Angular JS (sort, et c) . 2. This is based on current functionality of ARMS . Any new additons will need to be estimated seperately . 3. GLobal Logon needs to be implemented as per latest AT&T direction and solution . 4. Build deployment process to users Machine will not be applicable and as ARMS GUI will be a web Application in Azure 5. Certifcate provisioning and configuration for Web App 6. ARMS is a complex activeX application using legacy tools like TDBGrid to display tabular data from database contents through means of a TDataSet for which support is no longer avaialble 7. Implementing replacement for TDBgrid which is curretly being used in most of the screens for ARMS in Angular , ActiveX and adding suport for Excel ,pdf ,word libraries along with Grid replacement 8. GUI application has over 158(Approx) screens, these have been categorized based on complexity. 70 screens are highly complex. 49 screens are of medium complexity and 39 of low complexity. 9. Apart from these are numerous pop-ups and alerts that are used by the application along with complex toolbar having support for word ,excel ,pdf which has to be integrated with TDBgrid replacement in Angular and Spring Boot 10 . A highly complex screen has numerous UI elements with complex business logix to be implemented which includes read and write operation to the huge DB at backend (250hrs /screen is the average estimate considering reuse and creation of framework and unit testing) 11.There are around 49 screens having the business logic which is of medium complexity. (150hrs /screen is the average estimate considering reuse and creation of framework ) 12.The changes to the code includes efforts to change the front end component to Angular and the backend component to Spring. 13.There are currently more than 700 C/C++ source and header files that needs to be rewritten Each and every functionality needs to be unit tested as part of Code Rewrite which is needed . 14. Report Utility functinality will also need to be rewritten assumtions and ARMS GUI related assumtions (functinality wise) . | Refer GUI Breakdown for sheet details
ARMS WebApplication migration from Windows Server to Linux. | NA | This functionality will not be needed in Azure , as ARMS desktop app will be rewritten to a web app which is estimated sepeartely .
Update SSIS compatibility level for latest Windows 2016 version. | 2250 | 1. passwords need to be encrypted in tables (currently plain text ) used by for 150 + SSIS packages 2. Connectvity Managers need to be migrated to a solution level 3. Upgrade SSIS Packages from Package Deployment Model to Project Deployment Model 4. Modify Stored Procedures to support consistent compatibility levels across envs in Azure & Unit test the changes 5. This includes the DMT SSIS packages and Server Jobs 6. Restructure of Import functionality to work with Azure Files
Set-up ARMS database in Azure. | 300 | 1. Assuming ADBA and Migration DB will be setting up and migrating data & Jobs setup to Azure .DB objects migration to be done by ADBA/Migration DBA for all env 2. DB drivers setup and configuraion (SQL , teradata ,Oracle) will be taken up my ADBA/Migration DBA team . 3. Link server and related configuration to be done by ADBA/Migration DBA team 4. App related config changes in code , SSIS packages (100+), Batch Jobs to be done by App team and Basic connectvity test with DB in Azure env
Application updates to implement move application log to Azure application Insights & Alerts. | 300 | 1. Provisioning and configure Application Insights so that application logs can be logged in one place but still can be queried independently will be done by Migration team 2. Configure Azure Monitor and Azure Alerts for common operational alerts to be done by Migration Team 3. Application code to handle Inetgration with App Insights using SDKs will be implemented by Application team
Interface Impacts and efforts for Arms (Encryption) | Hours | Assumptions | Comments
Implement changes for C:D Secure Plus. Refactor Data Router for Azure | 1860 | 1. Encrytpion of all CD ,ASLA ,ODBC connections and fileshare with Interfaces . Assuming installation,setup and certificate configuration will be done by GSI team for CD secure Plus for CD interfaces . Application team will provide config to GSI team and do the testing with interface team 2. Data router interfaces setup and configuration to be done by GSI team . App team to provide configuration and do Interface Testing 3. This doesnt cover interfacing application efforts for migration to azure | Refer Interfaces sheet for breakdown
Cloud specific Efforts
Requirement/Feature/User Story Grooming | 150 | Create App Modernization User Stories and Sprint planning
| 150 | US grooming with Acceptance criteria and scope for each Sprint
Build Deployment and Support for POC env
Build/Deployment Support | 100 | 1.Provide application binaries 2. Assistance to Migration team in installation & configuration steps for Application modules
Test Result Validation | 300 | 1. POC env sanity test for 40+ Interfaces and App functionality 2. Resolve issues with Migration team in POC env 3.Submitting EFORCS for all 40+ Interfaces (prod and Non Prod) after gathering Info
Mylogins Onboarding | 150 | Onboard Mylogins in Azure and integration for automated provisioning
Application updates to implement move application secrets and configuration files to Azure Key Vault | 400 | 1. Move application secrets (passwords, DB config) from Hardcoded and configuration files to KeyVault . 2. Key Vault implementaion for App service (ARMS GUI) 4. Key Vault Implementation for Batch scripts (100+) 5. Assuming that SSIS packages will not be fetching Secrets from Key Vault
Azure CI Pipeline & DevOps set-up | 300 | Implement Devops Piepline in Azure using Azure Dev Ops repository
Netcool updates | NA | EMAS team will be sharing there impacts
Migration Acceptance and Testing
Smoke and Connectivity Testing | 150 | 1. Review Smoke test plan 2. Provide support during smoke test (ex. defect analysis, debug connectivity issues, etc.)
MAT Planning & execution | 2500 | 1. MAT plan and execuation for Development TCs . Includes website and Inetrafce Tesing also along with logging validations etc 2. Dev Support to other Teams in MAT planning & execution review 3. Fix defects and issues found during MAT testing
Cutover to Production - Go Live
Provide information & validate the Deployment/Cutover activities | 80 | Application Deployment plan , Cutover meetings , Planning
Perform changes in support of redirecting traffic (Application Specific) | 40 | Cutover execuation and Support
Cutover traffic validations (UAT/Friendly Testing) Only applicable for Canary deployments |  | NA
30-Day Warranty Period | 400 | Warranty support post cutover

## Interface Impacts
Interface Name | Source | Target | Hours | Assumptions | Notes
ACIS (3940) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
AIM (2397) | Mainframe File access (RACF) | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team | Mainframe interface . Need to be checked
AIRS (3809) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
AspectAOD (20943) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ATBS (13806) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ATWS (21685) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
BEST (17599) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
Billing Consolidator (14972) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CABS-AIT (3935) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CABS-N (23308) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CABS-PB (1178) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CABS-SE (20977) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CABS-SW (1174) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CASH (15860) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CENET (2022) | ODBC | ODBC | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CENT (20616) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team | Mainframe interface . Need to be checked
CIA ABS (13585) | File Share | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CPE Billing (5337) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CRIS (7882) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CRIS CASH (1551) | Connect Direct | Connect Direct Secure+ | NA | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
DCS (13804) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ECS (14883) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
EDD (17689) | Data router | data Router | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
EXECUBILL (17020) | connect Direct | connect Direct Secure+ | NA |  | Retired
GISDN (18756) | file Share | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ISB (14084) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
JDE (12627) |  |  | NA |  | Retired
Oracle ART (16350) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
PD Track (19255) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
RBS (3958) | Manual export to local file system | TBD | 50
RPMS (13490) | file Share | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
SDN-ONENET (13715) | file Share | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
TAXI (578) | DB Connection ODB | DB Connection ODB | 40 | DB connection is setup through SSIS packages.Assuming that SSIS packages will not be fetching Secrets from Key Vault (technically not feasible).
THRIFTY - AS400 (13261) | Connect Direct | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
TLD-PROD (7547) | DB Connection ODB | DB Connection ODB | 40 | DB connection is setup through SSIS packages.Assuming that SSIS packages will not be fetching Secrets from Key Vault (technically not feasible).
UNIVERSAL BILLER RESULTS (14191) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
VTNS (13440) | file Share | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
WEBTAXI (8685) | DB Connection ODB | DB Connection ODB | 40 | DB connection is setup through SSIS packages.Assuming that SSIS packages will not be fetching Secrets from Key Vault .
ADAPT (21656) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
AIRS (3809) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ASLA (28558) | Data router | Data Router | 50 | Data router interfaces setup and configuration to be done by GSI team . App team to provide configuration and do Interface Testing
ATT MACS (8182) | connect Direct | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CCAX (19704) | connect Direct | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
CCProcMech (21030) | Connect Direct | Connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
ExClaim (10427) | DB Connection ODB | DB Connection ODB | 40 | DB connection is setup through SSIS packages.Assuming that SSIS packages will not be fetching Secrets from Key Vault (technically not feasible).
LRS (8937) |  |  | NA |  | Retired
WEBPHONE (13924) | db Connection ODB | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
MPLTOOLS (24511) | File Share + cd | connect Direct Secure+ | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
OARS (14273) | Connect Direct + DB connection | Connect Direct sec + (+) DB connection | 50 | Assuming installation,setup and certificate configuration will be done by GSI team. Application team will provide config to GSI team and do the testing with interface team
Total |  |  | 1860

## ARMS GUI rewrite Ananlysis
| Screens | Complexity | Notes |  | Components | Number of C++ Files | Header Files | Total Files
| Main |  |  |  | Armsapplication | 267 | 289 | 587
1 | Main login screen for ARMS | High | This is currently having global logon integration along with DB connectivity to respective envionemnet being selected . |  | ArmsExcelAutomation |  |  | 19
2 | Main Screen after Login - Query tab | Medium |  |  | ArmsFuncs |  |  | 79
3 | Maintaince Tab | Medium |  |  | ReportUtility | 49 | 52 | 120
4 | User Adminitration Tab | Medium |  |  | Report Generator |  |  | 28
5 | Table Maint tab - | Medium
6 | Transfer Tab | Medium | GUI screen is east to implemet but complex functionality wise so keeping Medium and High for inner screens |  | Others
7 | Management Tab | Low |  |  | Excel suport
8 | Reports Tab | Low |  |  | Global logon DLL
9 | Profiles | High |  |  | PDF supoirt libs and resources
10 | Tool bar with icons | High | This will keep on changing based on user and its seelction
11 | Run Default Profile | High
12 | Report Utility | Very High | This is a single screen but highly complex separate component in itself will add hours based on discussion with Terry |  | Entire GUI operates on SPs present in DB which counts to approxminate 400 in number
2 | Main Screen after Login - Query tab |  |  |  | High | 250
2.1 | Customer Search | High |  |  | Medium | 150
2.2 | ACNA | High |  |  | Simple | 50
2.3 | AECN | High
2.4 | OCN | High
2.5 | CTC | High
2.6 | ACCT?INV/FAN | High
2.7 | BILL NAME | High
3 | Maintaince Tab
3.1 | Contacts | Medium
3.2 | Contacts AP Sub Group | High | It Iinvoles tdb Grid
3.3 | Account AP Sub Group | Medium
3.4 | Manage Template Notes | High
4 | User Adminitration Tab
| User Maintaince | High
| User Admin Reports with Export to Excel functiality | Medium
| Roles/Task Assignment | High
| Report Hirachy Miantaince | High
| Add change role screen in User Maintaince | High
5 | Table Maint tab
| Xref3 Maintaince | High
| Xref3 History Maintance | High
| Segment Maintance | High
| Letter Profile Maintaince | High
| ACNA Maintaince | High
| AECN Maintaicne | High
| Customer Maintaince | High
| Message Maintaince | High
| Customer Usage | High
| Sub Activities Maintaince | High
6 | Transfer Tab
Cusotmter Transer
Notes Transer
7 | Management Tab
7.1 | Notes Activity Report | High
7.2 | Outsatdnign Bring up Reports | Low
7.3 | Payment Terms Update | Medium
7.4 | Notes Activity Managers Report | High
7.5 | Open Flag Activity Report | High
8 | Reports
8.1 | Report Utility GUI launch Screen | high
9 | Profiles
9.1 | Manage Profiles | High
9.2 | Clear Slection | Medium
7.1 | Notes Activity Report
| Notes Activity Report Filter | High
| Notes activity Report Filter Aged Dtl | High
7.2 | Outsatdnign Bring up Reports
| Outsatdnign Bring up Reports Popup | Low
| Outsatdnign Bring up Reports Export to Excel | High | It involes external Excel library support migrating all the data
7.3 | Payment Terms Update
| Payment Terms Update Filter | Medium
| Search by Account Number | Low
| Search by Customer | Medium
| Payment Terms Update Result Grid | Medium
| Update Payment Term | Medium
7.4 | Notes Activity Managers Report
| Notes Activity Report Filter | High
| Notes activity Report Filter Aged Dtl | High
7.5 | Open Flag Activity Report
| Popup Window | Low
| Export to Excel Functionality | High | It involes external Excel library support migrating all the data
2.1 | Customer Search |  | Please note all of the screens has to be integrated with other search Critires of Query searches as well so I am not repeating them for all but they have to be integraated over 7 tabs
2.1.1 | Aged Dtl grid with search results | High
2.1.2 | Different tabs on Aged dtl grid with similar functionality | High
| Summary Tab | Medium
| Cusomer Notes Tab | Medium
| Account Notes Tab | Medium
| Internal Contacts | Medium
View EMAOR
| View Update Conatcts | Medium
| Letter Functionality | High
| Rep Copy | Medium
| CPPO | Medium
| Export To Excel( Bankrupcy) | High
| Invoice View | High
| Transpose View | High
| Export To Excel | High
| Email Functioanlity | High
| Account Details update | High
| Commitment Histpry Report | Low
| Commitemnt amout screen in account details update | Medium
| Contested amount screen in accnt details update | Medium
| Random screns in Account detils update | Medium
| Popus at different screns | Low
| Mail Field update | Low
| Email Merge | Medium
| Options on account details update trhu grid | High
| Past Due amount screen on double clicking account number | Medium
| Add note in account notes | Medium
| Modify | Medium
| Delete | Medium
| Resolve | Medium
| Contacts | Medium
| Perm not | Medium
| History | Medium
| Add note in Customer notes | Medium
| Modify | Medium
| Delete | Medium
| Resolve | Medium
| Contacts | Medium
| Perm not | Medium
| History | Medium
| Cancel Letter in account notes | Medium
| Cancel Letter in cusomter notes | Medium
Transfer Tab
6.1 | Cusomter Transfer | High | GUI screen is east to implemet but complex functionality wise so keeping High
6.2 | Notes transfer | High | GUI screen is east to implemet but complex functionality wise so keeping High
Letter Profile Maintaince
| Create | High
| Modify | High
| Delete | Medium
| Seelct profile to Modify Screen | Medium
Cusotomer Maintance
| Different options on Grid | High | Inlcudes various functionalites which needs to be integrated with TDBGrid
Customer Xref3 Maint
| ACNA | High
| AECN | High
| Query | High
| Report to Excel | High
| Random | High
| Customer | High
| Results after Qry | High
Customer Xref3 Maint History
| ACNA | High
| AECN | High
| Query | High
| Report to Excel | High
| Random | High
| Customer | High
| Results after Qry | High
Report Utility
| Main Report Screen | High | 250
| Canned reports | Low | 1500 | 50 hours per report . 30 reports active
| Template reports | Medium | 600 | 4 reports .150 Hours per report
| Login of report Utility | High | 250
1 | Main login screen for ARMS | High | 250
2 | Main Screen after Login - Query tab | Medium | 150
3 | Maintaince Tab | Medium | 150
4 | User Adminitration Tab | Medium | 150
5 | Table Maint tab - | Medium | 150
6 | Transfer Tab | Medium | 150
7 | Management Tab | Low | 50
8 | Reports Tab | Low | 50
9 | Profiles | High | 250
10 | Tool bar with icons | High | 250
11 | Run Default Profile | High | 250
12 | Report Utility | Very High
2 | Main Screen after Login - Query tab
2.1 | Customer Search | High | 250
2.2 | ACNA | High | 250
2.3 | AECN | High | 250
2.4 | OCN | High | 250
2.5 | CTC | High | 250
2.6 | ACCT?INV/FAN | High | 250
2.7 | BILL NAME | High | 250
3 | Maintaince Tab
3.1 | Contacts | Medium | 150
3.2 | Contacts AP Sub Group | High | 250
3.3 | Account AP Sub Group | Medium | 150
3.4 | Manage Template Notes | High | 250
4 | User Adminitration Tab
| User Maintaince | High | 250
| User Admin Reports with Export to Excel functiality | Medium | 150
| Roles/Task Assignment | High | 250
| Report Hirachy Miantaince | High | 250
| Add change role screen in User Maintaince | High | 250
5 | Table Maint tab
| Xref3 Maintaince | High | 250
| Xref3 History Maintance | High | 250
| Segment Maintance | High | 250
| Letter Profile Maintaince | High | 250
| ACNA Maintaince | High | 250
| AECN Maintaicne | High | 250
| Customer Maintaince | High | 250
| Message Maintaince | High | 250
| Customer Usage | High | 250
| Sub Activities Maintaince | High | 250
6 | Transfer Tab
Cusotmter Transer
Notes Transer
7 | Management Tab
7.1 | Notes Activity Report | High | 250
7.2 | Outsatdnign Bring up Reports | Low | 50
7.3 | Payment Terms Update | Medium | 150
7.4 | Notes Activity Managers Report | High | 250
7.5 | Open Flag Activity Report | High | 250
8 | Reports
8.1 | Report Utility GUI launch Screen | high | 250
9 | Profiles
9.1 | Manage Profiles | High | 250
9.2 | Clear Slection | Medium | 150
7.1 | Notes Activity Report
| Notes Activity Report Filter | High | 250
| Notes activity Report Filter Aged Dtl | High | 250
7.2 | Outsatdnign Bring up Reports
| Outsatdnign Bring up Reports Popup | Low | 50
| Outsatdnign Bring up Reports Export to Excel | High | 250
7.3 | Payment Terms Update
| Payment Terms Update Filter | Medium | 150
| Search by Account Number | Low | 50
| Search by Customer | Medium | 150
| Payment Terms Update Result Grid | Medium | 150
| Update Payment Term | Medium | 150
7.4 | Notes Activity Managers Report
| Notes Activity Report Filter | High | 250
| Notes activity Report Filter Aged Dtl | High | 250
7.5 | Open Flag Activity Report
| Popup Window | Low | 50
| Export to Excel Functionality | High | 250
2.1 | Customer Search
2.1.1 | Aged Dtl grid with search results | High | 250
2.1.2 | Different tabs on Aged dtl grid with similar functionality | High | 250
| Summary Tab | Medium | 150
| Cusomer Notes Tab | Medium | 150
| Account Notes Tab | Medium | 150
| Internal Contacts | Medium | 150
| View EMAOR | Medium | 150
| View Update Conatcts | Medium | 150
| Letter Functionality | High | 250
| Rep Copy | Medium | 150
| CPPO | Medium | 150
| Export To Excel( Bankrupcy) | High | 250
| Invoice View | High | 250
| Transpose View | High | 250
| Export To Excel | High | 250
| Email Functioanlity | High | 250
| Account Details update | High | 250
| Commitment Histpry Report | Low | 50
| Commitemnt amout screen in account details update | Medium | 150
| Contested amount screen in accnt details update | Medium | 150
| Random screns in Account detils update | Medium | 150
| Popus at different screns | Low | 50
| Mail Field update | Low | 50
| Email Merge | Medium | 150
| Options on account details update trhu grid | High | 250
| Past Due amount screen on double clicking account number | Medium | 150
| Add note in account notes | Medium | 150
| Modify | Medium | 150
| Delete | Medium | 150
| Resolve | Medium | 150
| Contacts | Medium | 150
| Perm not | Medium | 150
| History | Medium | 150
| Add note in Customer notes | Medium | 150
| Modify | Medium | 150
| Delete | Medium | 150
| Resolve | Medium | 150
| Contacts | Medium | 150
| Perm not | Medium | 150
| History | Medium | 150
| Cancel Letter in account notes | Medium | 150
| Cancel Letter in cusomter notes | Medium | 150
Transfer Tab
6.1 | Cusomter Transfer | High | 250
6.2 | Notes transfer | High | 250
Letter Profile Maintaince
| Create | High | 250
| Modify | High | 250
| Delete | Medium | 150
| Seelct profile to Modify Screen | Medium | 150
| Cusotomer Maintance | High | 250
| Different options on Grid | High | 250
Customer Xref3 Maint
| ACNA | High | 250
| AECN | High | 250
| Query | High | 250
| Report to Excel | High | 250
| Random | High | 250
| Customer | High | 250
| Results after Qry | High | 250
Customer Xref3 Maint History
| ACNA | High | 250
| AECN | High | 250
| Query | High | 250
| Report to Excel | High | 250
| Random | High | 250
| Customer | High | 250
| Results after Qry | High | 250
26800